## Checklist
Major Features | Description | Author PoV Owning Teams | API's | Core Owning Teams for Each API | Architeture Review | Estimation | Funding | Targeted Dev Timelines | SIT Timelines | Remarks
MF1 | Ability for pharmacy claims submitted for Author by Humana members on the HPS system to be provided to the HPDI Patient Access API for the EOB Pharmacy Profile. This should include payment and member cost information when available. | CDF | ExplanationofBenefit FHIR API - Adjudicated Claims - Provider Payment & Member Cost (Actual Cost Pharmacy) | API2 CDF | [5 empty] | Sonya Ash (API2) - Delivery date from her are awaited
MF2 | Ability for clinical information stored in the MRM system for Author by Humana members to be provided to the HPDI Patient Access API for any US Core Clinical Profile including Allergies, Social History, Nar. Extract, Vital Signs, Goals, Medications, Problems, Plan Cares, Immunizations, Wellness Assessments, and Results. | MRM/CDF | Immunization FHIR API -Immunization (USCDI) | Siddhartha Jakkamreddy to confirm | [5 empty] | Arhcitecture discussion is pending. Sid to schedule follow up meeting (MRM). MRM tech team is currently working to publish 11 data topics to meet this requirement and Author will also subscribe to these. Author requires CDF team to filter by platform code so that only Author managed member data is published for consumption.
|  |  | MedicationRequest FHIR API - Medications (USCDI) | Siddhartha Jakkamreddy to confirm
|  |  | AllergyIntollerance FHIR API -Allergies and Intolerance (USCDI) | Siddhartha Jakkamreddy to confirm
|  |  | CarePlan FHIR API - Assessment and Plan of Treatment (USCDI) | Siddhartha Jakkamreddy to confirm
|  |  | Diagnostic Report Profile for Report and Note Exchange FHIR API - Clinical Notes | Siddhartha Jakkamreddy to confirm
|  |  | Goal FHIR API - Goals (USCDI) | Siddhartha Jakkamreddy to confirm
MF3 | Ability for Author by Humana members to be provided to the HPDI Patient Access API for any US Core Clinical Profile including Laboratory and Vital Signs. | Core Clinical | Observation FHIR API (focusing on Laboratory Results, Vital Signs, and Smoking Status) - Laboratory (USCDI) - Smoking Status (USCDI) - Vital Signs (USCDI) | NA | [5 empty] | Lab and Vitals. Author IT own this feature. Completed - CC observations API Author to do work with MRM to dedup
MF4 | Ability for drug formulary information defined for Author by Humana benefit plans to be provided to the HPDI Patient Access API for the DaVinci PDEX formulary profiles. | XC/CDF | Drug Formulary API (DaVinci) - Drug Formularies (Specific to Part D MA Plans) | Siddhartha Jakkamreddy to confirm | [5 empty] | MF4 needs a follow up meeting (TBC)
MF5 | Ability for provider directory information for medical, dental, vision and pharmacy providers associated with Author by Humana benefit plans to be provided to the DaVinci PDEX plan net profiles. | XC/CDF | Provider Directory API (DaVinci) - Provider Directory | TBC | [5 empty] | MF5 is waiting on Cillie/Jennifer V
|  | XC/CDF | Provider Directory API (DaVinci) - Pharmacy Directory | TBC | [5 empty] | MF5 is waiting on Cillie/Jennifer V