## Risks
RISKS
Risk No. | Date Identified | Reported By | Description | Probability | Impact | Preventative Actions | Contingent Actions | Mitigation Options | Owner | Actions By | Target Date | Status | Notes
1 | 2021-02-25 | Sarah Taylor | Provider Directory: Assuming Author can proxy the Humana Core endpoint via Author Apigee portal. Author does not have a target date from Core on when this will be available to do a feasibility check to ensure the proxy will technically work. |  |  |  |  | Find another Core endpoint to do POC. |  |  |  | Open
2 | 2021-03-04 | Charles Southworth | Clinical Notes: Per Chris C., if we don't exclude, Author may end up with a people/process work effort that all existing Notes need to be cleaned up as a result or similar. Not sure what the volume is, but whatever it is will get bigger over time. | [8 empty] | Open
3 | 2021-03-05 | Charles Southworth | API for Directories (Pharmacy & Provider) is listed as at risk for 7/1 delivery by CORE. | 75% |  |  |  |  | Sarah Taylor |  |  | Open | Will bring this up in the HPDI tech meeting - need a plan here. Need commitment from Core on who is assinged to do the work; need escalation

## Actions
ACTIONS
Action No: | Date Raised | Area | Priority | Description | Action By | Deadline | Progress | Status

## Issues
Issues
Issue No. | Priority | Description | Owner | Cause | Resolution | Status | Comments | Target Date

## Decisions
Decisions
Decision No: | Date Opened | Raised By | Description | Category | Status | Clarification | Approver/Decision Maker | Date Closed | Channel | Notes
1 | 2021-02-18 |  | The claims data topic is the existing data exchange that UST has built to publish claims data out for Humana Core to consume. | System of Record | Closed | Leverage the existing claims data topic to meet HDPI requirements. | Nikki Woodcox | 2021-02-25 | Teams Chat | Teams Chat
2 |  | Sarah Taylor | Smoking Status: We do not believe this data is maintained by Author. It appears to come as part of an antiquated system and we are specifically forbidden from gathering this data from members during intake. | Compliance | Open |  | Helena Rawson |  | Email
3 |  |  | Determine if data should be loaded as 'batch' or 'on demand'? | Tech | Open |  | Sumana Bellary
4 | 2021-02-25 |  | What is the source for member data? | System of Record | Closed | HRDW will be used as the source for member data. | Sarah Taylor | 2021-02-25 | Teams Chat | Teams Chat
5 |  |  | Is a VSR needed for Core? |  | Pending |  | Sarah Taylor |  |  | Need business approval; Sarah sent V1or v2 to Pam & Chris C
6 | 2021-02-20 |  | Core is deriving this info from claims data but suspect we want to leverage OML to meet this requirement. I am not clear on exactly why core is not using OML but can try to poke and prod for more info. Are we all aligned that Author will proceed with using OML to meet this requirement or do we need to have additional discussions to make the decision final? | System of Record | Closed | Author will use OML. | Pam Bell | 2021-02-25 | Email | Email
7 | 2021-03-04 | Sarah Taylor | Health Concerns vs Problems: What we have captured in Sugar is closer aligned to the definition for 'Health Concerns' data subject rather than 'Problems'. | Compliance | Pending |  | Helena Rawson |  | Email | Chris C. can show Helena the specific screen where this info is populated in case it would be helpful. Sarah included the link to this specific guidance and definitions below for reference. https://www.hl7.org/fhir/us/core/ValueSet-us-core-condition-category.html
8 | 2021-03-04 | Sarah Taylor | Clinical Notes: We currently capture notes in Sugar but they were never intended to be exposed to patients. Our request is that we do not categorize these as Clinical Notes and not expose as part of HPDI initiative. | Compliance | Pending |  | Helena Rawson |  | Email | Suggested by Chris C. in the past: Exclude them from FHIR as they aren't actually clinical. Give the team a heads up that they WILL be included ASAP. They will need to adjust their people/process as a result and also go scrub existing notes.
9 | 2021-03-09 | Tim Doyle (Architecture) | Member identifier is entity ID and AUthor will provide member card ID on the coverage level | System of Record | Closed | This is a better member indentifier than using membGenKey - the | Tim Doyle
10 | 2021-03-09 | Sarah Taylor | Mavenwave - Need an architecture recommendation - how we handle merging data from two sources, two sources systems into the FHIR store? | Tech | Open | MavenWave is the recommender | Sumana Bellary

## Dropdowns
Dropdowns
To change menu items simply edit the Menu and Description fields below.
Actions
Field | Menu | Description
Priority | High | Complete in 1 - 2 days
| Medium | Complete in 1 week
| Low | Complete in 1 to 2 weeks
Status | Open | In progress
| Pending | Waiting on action by another party
| Resolved | Resolved pending agreement from customer/sponsor
| Closed | Closed as agreed by customer/sponsor
Risks
Field | Menu | Description
Probability | High | Very likely that this risk will occur/happen.
| Medium | 50/50 chance that this risk will occur.
| Low | Low probability that this risk will occur.
Impact | High | This would badly impact the project e.g. cost, delay, quality.
| Medium | A manageable impact on the project.
| Low | A low impact on the project.
Status | Open | In progress
| Pending | Waiting on action by another party
| Closed | Closed as agreed by customer/sponsor
Issues
Field | Menu | Description
Priority | High | This issue must be resolved for progress to be made.
| Medium | This impacts the project, but doesn’t stop progress.
| Low | A low impact on the project. Perhaps optional to fix.
Status | Open | In progress
| Pending | Waiting on action by another party
| Resolved | Resolved pending agreement from customer/sponsor
| Closed | Closed as agreed by customer/sponsor